## WBS Outline & Diagram
Work Breakdown Structure
PROJECT TITLE | My Campus Marketplace | COMPANY | SCTCC CMSC 2279-22
PROJECT MGR | Group 1 | DATE | 2024-02-03
OUTLINE |  |  | OUTLINE |  | OUTLINE
1 | Initiation |  | 3 | Execution | 5 | Close
1.1 | Project Charter |  | 3.1 | Development and Coding | 5.1 | Final Deployment
1.1.1 | Define scope and objective |  | 3.1.1 | Setup development enviroment | 5.1.1 | Deploy the web and mobile app
1.1.2 | Identify key stakeholders |  | 3.1.2 | Code web and mobile app components | 5.1.2 | Conduct post-deployment review
1.1.3 | Establish project team |  | 3.1.3 | Conduct code reviews | 5.2 | Project Documentation
1.1.4 | Outline high-level project timeline |  | 3.2 | Testing | 5.2.1 | Finalize and archive all project documentation
1.2 | Initial Risk Assessment |  | 3.2.1 | Perform unit testing | 5.2.2 | Document lessons learned
1.2.1 | Identify potential risks |  | 3.2.2 | Conduct integration testing | 5.5 | Project Closure
1.2.2 | Perform preliminary risk analysis |  | 3.2.3 | Execute user acceptance testing | 5.5.1 | Release project resources
2 | Planning |  | 3.3 | Deployment Preperation | 5.5.2 | Conduct closure meeting with stakeholders
2.1 | Detailed Project Plan |  | 3.3.1 | Develop deployment plan
2.1.1 | Develop detailed project schedule |  | 3.3.2 | Prepare user manuals and documentation
2.1.2 | Define resource allocation |  | 4 | Monitoring
2.1.3 | Establish budget and financial plan |  | 4.1 | Progress Tracking
2.2 | Technical Specifications |  | 4.1.1 | Monitor project milestones against the plan
2.2.1 | Define technicaal requirements for web and mobile app |  | 4.1.2 | Conduct regular status meetings
2.2.2 | Create system architecture diagrams |  | 4.2 | Quality Assurance
2.3 | Risk Management Plan |  | 4.2.1 | Perform continuous testing
2.3.1 | Develop strategies for identified risks |  | 4.2.2 | Implement quality control measures
2.3.2 | Plan for ongoing risk monitoring |  | 4.3 | Risk Monitoring
|  |  | 4.3.1 | Track and manage risks
|  |  | 4.3.2 | Update risk management plan as needed
CREATE MY CAMPUS MARKETPLACE
1 Initiation
1.1 Project Charter
1.2 Initial Risk Assessment
1.1.1 Define scope and objective
1.1.2 Identify Stakeholders
1.1.3 Establish Project Team
1.1.4 Outline high-level timeline
1.2.1 Identify potential risks
1.2.2 Perform preliminary risk analysis
2 Planning
2.1 Detailed Project Plan
2.2 Technical Specifications
2.3 Risk Management Plan
2.1.1 Develop Detailed schedule
2.1.2 Define resource allocation
2.1.3 Establish budget and financial plan
2.2.1 Define technical requirements
2.2.2 Create system architecture diagrams
2.3.1 Develop strategies for identified risks
2.3.2 Plan for ongoing risk management
3 Execution
3.1 Development and Coding
3.2 Testing
3.3 Deployment Preparation
3.1.1 Setup development enviroment
3.1.2 Code web and mobile app components
3.1.3 Conduct code reviews
3.2.1 Perform unit testing
3.2.2 Conduct integration testing
3.2.3 Execute user acceptance testing
3.3.1 Develop deployment plan
3.3.2 Prepare user manuals and documentation
4 Monitoring
4.1 Progress Tracking
4.2 Quality Assurance
4.3 Risk Monitoring
4.1.1 Monitor project milestones
4.1.2 Conduct regular status meetings
4.2.1 Perform continuous testing
4.2.2 Implement quality control measures
4.3.1 Track and manage risks
4.3.2 Update risk mangement plan as needed
5 Close
5.1 Final Deployment
5.2 Project Documentation
5.3 Project Closure
5.1.1 Deploye the web and mobile app
5.1.2 Conduct post-deployment review
5.2.1 Finalize and archive all project documentation
5.2.2 Document lessons learned
5.3.1 Release project resources
5.3.2 Conduct closure meeting with stakeholders